## Inventory
Type | Description | T | W | Length | PO Qty | CO Qty | PO+CO Qty | Unit Cost | LF (Linear Ft) | BF/SF | Total Cost | Total Cost+Tax | 2026-06-18 | Invoice # | Total Delivered | Delivered LF | Delivered BF/SF | Delivered Cost | Delivered Cost+Tax | Remaining Qty | Remaining LF | Remaining BF/SF | Remaining Cost | Remaining Cost+Tax | Leftover LF (Site) | Material Used LF | Material Used Cost
Lumber | 1 x 4 1 PT | 1 | 4 | 1 | 3113 | 0 |  | 1595 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 1 PT | 2 | 4 | 1 | 21738 | 0 |  | 950 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 12 PT | 2 | 4 | 12 | 1557 | 0 |  | 950 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 PT | 2 | 6 | 1 | 13123 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 PT | 2 | 6 | 1 | 297 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 8 PT | 2 | 6 | 8 | 78 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 10 PT | 2 | 6 | 10 | 91 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 12 PT | 2 | 6 | 12 | 564 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 1 PT | 2 | 8 | 1 | 229 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 12 PT | 2 | 8 | 12 | 1344 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 1 PT | 2 | 10 | 1 | 3423 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 1 PT | 2 | 12 | 1 | 174 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 8 PT | 2 | 12 | 8 | 60 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 8 PT | 2 | 12 | 8 | 138 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 10 PT | 2 | 12 | 10 | 460 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 12 PT | 2 | 12 | 12 | 95 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 12 PT | 2 | 12 | 12 | 264 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 14 PT | 2 | 12 | 14 | 38 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 16 PT | 2 | 12 | 16 | 290 | 0 |  | 1300 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 1 x 4 1 DFL#2 | 1 | 4 | 1 | 40102 | 0 |  | 1100 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 1 x 6 1 DFL#2 | 1 | 6 | 1 | 21847 | 0 |  | 1100 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 1 x 8 12 DFL#2 | 1 | 8 | 12 | 252 | 0 |  | 1100 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 1 DFL#2 | 2 | 4 | 1 | 262387 | 0 |  | 680 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 1 DFL#2 | 2 | 4 | 1 | 64464 | 0 |  | 680 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 12 DFL#2 | 2 | 4 | 12 | 816 | 0 |  | 680 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 12 DFL#2 | 2 | 4 | 12 | 2600 | 0 |  | 680 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 DFL#2 | 2 | 6 | 1 | 185067 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 DFL#2 | 2 | 6 | 1 | 25184 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 DFL#2 | 2 | 6 | 1 | 141 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 1 DFL#2 | 2 | 6 | 1 | 228 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 8 DFL#2 | 2 | 6 | 8 | 2783 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 8 DFL#2 | 2 | 6 | 8 | 201 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 12 DFL#2 | 2 | 6 | 12 | 2317 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 12 DFL#2 | 2 | 6 | 12 | 3743 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 1 DFL#2 | 2 | 8 | 1 | 13741 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 8 DFL#2 | 2 | 8 | 8 | 1836 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 8 DFL#2 | 2 | 8 | 8 | 2308 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 10 DFL#2 | 2 | 8 | 10 | 579 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 12 DFL#2 | 2 | 8 | 12 | 52 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 14 DFL#2 | 2 | 8 | 14 | 26 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 8 12 DFL#2 | 2 | 8 | 12 | 1465 | 0 |  | 710 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 1 DFL#2 | 2 | 10 | 1 | 26961 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 8 DFL#2 | 2 | 10 | 8 | 840 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 8 DFL#2 | 2 | 10 | 8 | 21 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 10 DFL#2 | 2 | 10 | 10 | 98 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 12 DFL#2 | 2 | 10 | 12 | 319 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 10 14 DFL#2 | 2 | 10 | 14 | 3 | 0 |  | 845 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 8 DFL#2 | 2 | 12 | 8 | 5 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 8 DFL#2 | 2 | 12 | 8 | 70 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 10 DFL#2 | 2 | 12 | 10 | 147 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 12 DFL#2 | 2 | 12 | 12 | 398 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 12 DFL#2 | 2 | 12 | 12 | 26 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 14 DFL#2 | 2 | 12 | 14 | 89 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 16 DFL#2 | 2 | 12 | 16 | 257 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 12 18 DFL#2 | 2 | 12 | 18 | 35 | 0 |  | 1049 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 9 DFL#2 PET 104-5/8 | 2 | 4 | 9 | 25812 | 0 |  | 665 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 10 DFL#2 | 2 | 4 | 10 | 66 | 0 |  | 665 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 10 DFL#2 PET 116-5/8 (117-3/8) | 2 | 4 | 10 | 33165 | 0 |  | 675 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 10 DFL#2 PET 115-7/8 | 2 | 4 | 10 | 23671 | 0 |  | 675 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 12 DFL#2 | 2 | 4 | 12 | 3018 | 0 |  | 665 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 4 22 DFL#2 | 2 | 4 | 22 | 237 | 0 |  | 1495 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 9 DFL#2 PET 104-5/8 | 2 | 6 | 9 | 12626 | 0 |  | 722 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 10 DFL#2 PET 116-5/8 (117-3/8) | 2 | 6 | 10 | 12711 | 0 |  | 755 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 10 DFL#2 PET 115-7/8 | 2 | 6 | 10 | 12708 | 0 |  | 755 |  |  |  |  | 0 | [11 empty] | 0
Lumber | 2 x 6 22 DFL#2 | 2 | 6 | 22 | 190 | 0 |  | 831 |  |  |  |  | 0 | [11 empty] | 0
LUMBER SUBTOTAL
LVL | 1-3/4 X 18 LVL | 1.75 | 18 | 12 | 4 | 0 |  | 10.65 |  | 0 |  |  | 4 | 60126015 | [7 empty] | 0 |  |  | 0
LVL | 3-1/2 X 9-1/4 GLB/LVL | 3.5 | 9.25 | 8 | 8 | 0 |  | 15.55 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 9-1/4 GLB/LVL | 3.5 | 9.25 | 8 | 4 | 0 |  | 15.55 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 9-1/4 GLB/LVL | 3.5 | 9.25 | 12 | 6 | 0 |  | 15.55 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 8 | 7 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 10 | 40 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 12 | 4 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 12 | 3 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 12 | 14 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 14 | 5 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 14 GLB/LVL | 3.5 | 14 | 8 | 2 | 0 |  | 22.85 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 8 | 2 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 10 | 10 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 12 | 17 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 14 | 16 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL | 3.5 | 16 | 14 | 9 | 0 |  | 25.1 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL | 3.5 | 16 | 18 | 25 | 0 |  | 25.1 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 18 GLB/LVL | 3.5 | 18 | 12 | 2 | 0 |  | 28.27 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 9-1/4 GLB/LVL | 5.25 | 9.25 | 10 | 3 | 0 |  | 23.75 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 11-7/8 GLB/LVL | 5.25 | 11.875 | 8 | 8 | 0 |  | 29.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 11-7/8 GLB/LVL | 5.25 | 11.875 | 10 | 42 | 0 |  | 29.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 11-7/8 GLB/LVL | 5.25 | 11.875 | 12 | 3 | 0 |  | 29.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 16 GLB/LVL | 5.25 | 16 | 12 | 4 | 0 |  | 37.45 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 16 GLB/LVL | 5.25 | 16 | 12 | 2 | 0 |  | 37.45 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 18 GLB/LVL | 5.25 | 18 | 20 | 2 | 0 |  | 41 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 18 GLB/LVL | 5.25 | 18 | 22 | 5 | 0 |  | 41 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 16 | 20 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 5-1/2 GLB | 3.5 | 5.5 | 10 | 31 | 0 |  | 5.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 5-1/2 GLB | 3.5 | 5.5 | 10 | 3 | 0 |  | 5.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 5-1/2 GLB | 3.5 | 5.5 | 12 | 5 | 0 |  | 5.6 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 5-1/2 GLB/LVL | 5.25 | 5.5 | 10 | 15 | 0 |  | 13.7 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 18 | 75 | 0 |  | 54 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 5-1/4 X 16 GLB/LVL PT | 5.25 | 16 | 18 | 7 | 0 |  | 54 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 12 | 1 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 11-7/8 GLB/LVL PT | 3.5 | 11.875 | 14 | 5 | 0 |  | 30.15 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 10 | 74 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL | 3-1/2 X 16 GLB/LVL PT | 3.5 | 16 | 12 | 9 | 0 |  | 40.95 |  | 0 |  |  | 0 | [8 empty] | 0 |  |  | 0
LVL SUBTOTAL
Each | 4" Sealer |  |  |  | 369 | 0 |  | 5 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | 6" Sealer |  |  |  | 258 | 0 |  | 5 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | 2X12 Gypsum Liner |  |  |  | 186 | 0 |  | 35.88 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | Sub Floor Adhesive |  |  |  | 2719 | 0 |  | 5.75 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | Steel C Channels |  |  |  | 93 | 0 |  | 13 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | Steel H Studs |  |  |  | 186 | 0 |  | 15.1 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | Alum Clips |  |  |  | 557 | 0 |  | 0.95 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
Each | Red Safety Rails |  |  |  | 1041 | 0 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 | 0
EACH SUBTOTAL
Panels | 15/32" APA Rated | 4 | 8 |  | 5197 | 0 |  | 499 | 0 |  |  |  | 500 | 60126015 |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 15/32 PT CDX | 4 | 8 |  | 974 | 0 |  | 1315 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 15/32 OSB/PLY | 4 | 8 |  | 2 | 0 |  | 499 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 15/32 OSB/PLY | 4 | 8 |  | 409 | 0 |  | 499 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 15/32 OSB/PLY | 4 | 8 |  | 55 | 0 |  | 499 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 15/32 OSB/PLY | 4 | 8 |  | 430 | 0 |  | 499 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 7/16" OSB | 4 | 8 |  | 75 | 0 |  | 479 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 7/16" OSB | 4 | 8 |  | 10638 | 0 |  | 479 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 7/16" OSB | 4 | 8 |  | 66 | 0 |  | 479 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 3/4" Ply | 4 | 8 |  | 7781 | 0 |  | 719 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 3/4" OSB or Ply | 4 | 8 |  | 347 | 0 |  | 719 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
Panels | 3/4" OSB or Ply | 4 | 8 |  | 464 | 0 |  | 719 | 0 |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 | 0 | 0
PANELS SUBTOTAL
GRAND TOTAL

## Change Orders
CO # | CO Date | Type | Description | T | W | Len | Qty Change | Unit Cost | Footage/SF | LF | BF/SF | Amount | Amount+Tax | Action | Matched PO Item

## Invoices
Invoice # | Date | Description | Type | T | W | Length | Qty Delivered | Delivered LF | Delivered BF/SF | Delivered Cost | Delivered Cost+Tax
60126015 | 2026-06-18 | 1-3/4 X 18 LVL | LVL | 1.75 | 18 | 12 | 4 | 48 | 0 | 511.2 | 511.2
60126015 | 2026-06-18 | 15/32" APA Rated | Panels | 4 | 8 |  | 500 | 0 | 16000 | 7984 | 7984