## BT Estimate
Category | Cost Code | Title | Cost Type | Unit Cost | Quantity | Unit | Builder Cost | Markup | Owner Cost | Mobilization | New Value | Source / Link
00 - General Conditions | 001 - Supervision | Site Supervision | Allowance | 18000 | 4 | Months | 72000 | 0.2 | 86400 | 2592 | 83808 | Qty: package/derived • Rate from Buyout [001]
00 - General Conditions | 004 - Site Office | Site Office | Allowance | 1500 | 4 | Months | 6000 | 0.2 | 7200 | 216 | 6984 | Qty: package/derived • Rate from Buyout [004]
00 - General Conditions | 005 - Housing | Housing - Management | Allowance | 15000 | 4 | Months | 60000 | 0.2 | 72000 | 2160 | 69840 | Qty: package/derived • Rate from Buyout [005]
00 - General Conditions | 006 - Forklift | Forklift | Equipment | 8000 | 4 | Months | 32000 | 0.2 | 38400 | 1152 | 37248 | Qty: package/derived • Rate from Buyout [006]
00 - General Conditions | 007 - Manlift | Manlift | Equipment | 7000 | 4 | Months | 28000 | 0.2 | 33600 | 1008 | 32592 | Qty: package/derived • Rate from Buyout [007]
00 - General Conditions | 008 - Crane | Crane | Equipment | 50000 | 1 | SF | 50000 | 0.2 | 60000 | 1800 | 58200 | Qty: package/derived • Rate from Buyout [008]
00 - General Conditions | 013 - Fuel | Fuel | Allowance | 1750 | 4 | Months | 7000 | 0.2 | 8400 | 252 | 8148 | Qty: package/derived • Rate from Buyout [013]
01 - Framing | 101 - Layout - Labor | Building I Layout - BLDG 1 | Labor | 0.25 | 25197 | SF | 6299.25 | 1.8 | 17637.9 | 529.137 | 17108.763 | Qty ='SRC-Estimate'!C30 • Rate from Buyout [101]
01 - Framing | 101 - Layout - Labor | Building II Layout - BLDG 1 | Labor | 0.25 | 25375 | SF | 6343.75 | 1.8 | 17762.5 | 532.875 | 17229.625 | Qty ='SRC-Estimate'!I30 • Rate from Buyout [101]
01 - Framing | 102 - Framing - Labor | Building I Wall Framing - BLDG 1 | Labor | 1.1 | 25197 | SF | 27716.7 | 1.5 | 69291.75 | 2078.7525 | 67212.9975 | Qty ='SRC-Estimate'!C30 • Rate from Buyout [102]
01 - Framing | 102 - Framing - Labor | Building II Wall Framing - BLDG 1 | Labor | 1.1 | 25375 | SF | 27912.5 | 1.5 | 69781.25 | 2093.4375 | 67687.8125 | Qty ='SRC-Estimate'!I30 • Rate from Buyout [102]
01 - Framing | 103 - Sheathing - Labor | Building I Sheathing - BLDG 1 | Labor | 0.25 | 25197 | SF | 6299.25 | 1.2 | 13858.35 | 415.7505 | 13442.5995 | Qty ='SRC-Estimate'!C30 • Rate from Buyout [103]
01 - Framing | 103 - Sheathing - Labor | Building II Sheathing - BLDG 1 | Labor | 0.25 | 25375 | SF | 6343.75 | 1.2 | 13956.25 | 418.6875 | 13537.5625 | Qty ='SRC-Estimate'!I30 • Rate from Buyout [103]
01 - Framing | 109 - Hardware - Labor | Building I Hardware - BLDG 1 | Labor | 0.25 | 25197 | SF | 6299.25 | 0.75 | 11023.6875 | 330.7106 | 10692.9769 | Qty ='SRC-Estimate'!C30 • Rate from Buyout [109]
01 - Framing | 109 - Hardware - Labor | Building II Hardware - BLDG 1 | Labor | 0.25 | 25375 | SF | 6343.75 | 0.75 | 11101.5625 | 333.0469 | 10768.5156 | Qty ='SRC-Estimate'!I30 • Rate from Buyout [109]
01 - Framing | 115 - Punchout - Labor | Building I Punchout - BLDG 1 | Labor | 0.2 | 25197 | SF | 5039.4 | 0.6 | 8063.04 | 241.8912 | 7821.1488 | Qty ='SRC-Estimate'!C30 • Rate from Buyout [115]
01 - Framing | 115 - Punchout - Labor | Building II Punchout - BLDG 1 | Labor | 0.2 | 25375 | SF | 5075 | 0.6 | 8120 | 243.6 | 7876.4 | Qty ='SRC-Estimate'!I30 • Rate from Buyout [115]
01 - Framing | 206 - Nails - Framing | Nails Framing | Labor | 0.65 | 50572 | SF | 32871.8 | 43.7403 | 1470693.522 | 44120.8057 | 1426572.7163 | Nails PLUG = contract − SUM(owner above) • Rate from Buyout [206]
01 - Framing | 201 - Lumber - Material | Building I Lumber Package - BLDG 1 | Material | 29.661 | 25197 | SF | 747368.217 | 0.3667 | 1021428.1422 | 30642.8443 | 990785.2979 | Qty: package/derived • Rate from Buyout [201]
01 - Framing | 201 - Lumber - Material | Building II Lumber Package - BLDG 1 | Material | 29.661 | 25375 | SF | 752647.875 | 0.3667 | 1028643.8508 | 30859.3155 | 997784.5352 | Qty: package/derived • Rate from Buyout [201]
01 - Framing | 205 - Hardware - Material | Building I Hardware Package - BLDG 1 | Material | 3.164 | 25197 | SF | 79723.308 | 0.1562 | 92176.0887 | 2765.2827 | 89410.806 | Qty: package/derived • Rate from Buyout [205]
01 - Framing | 205 - Hardware - Material | Building II Hardware Package - BLDG 1 | Material | 3.164 | 25375 | SF | 80286.5 | 0.1562 | 92827.2513 | 2784.8175 | 90042.4338 | Qty: package/derived • Rate from Buyout [205]
01 - Framing | 207 - Trusses - Material | Building I Truss Package - BLDG 1 | Material | 13.486 | 25197 | SF | 339806.742 | 0.1804 | 401107.8783 | 12033.2363 | 389074.6419 | Qty: package/derived • Rate from Buyout [207]
01 - Framing | 207 - Trusses - Material | Building II Truss Package - BLDG 1 | Material | 13.486 | 25375 | SF | 342207.25 | 0.1804 | 403941.4379 | 12118.2431 | 391823.1948 | Qty: package/derived • Rate from Buyout [207]

## SOV
Owners Invoices |  |  |  | Dist/line: | 107712.044
# | Scope | Type | Value
1 | Mobilization |  | 151722.4338
2 | Building I Layout - BLDG 1 | Labor | 124820.807
3 | Building II Layout - BLDG 1 | Labor | 124941.669
4 | Building I Wall Framing - BLDG 1 | Labor | 174925.0415
5 | Building II Wall Framing - BLDG 1 | Labor | 175399.8565
6 | Building I Sheathing - BLDG 1 | Labor | 121154.6435
7 | Building II Sheathing - BLDG 1 | Labor | 121249.6065
8 | Building I Hardware - BLDG 1 | Labor | 118405.0209
9 | Building II Hardware - BLDG 1 | Labor | 118480.5596
10 | Building I Punchout - BLDG 1 | Labor | 115533.1928
11 | Building II Punchout - BLDG 1 | Labor | 115588.444
12 | Building I Lumber Package - BLDG 1 | Material | 1098497.3419
13 | Building II Lumber Package - BLDG 1 | Material | 1105496.5792
14 | Building I Hardware Package - BLDG 1 | Material | 197122.85
15 | Building II Hardware Package - BLDG 1 | Material | 197754.4778
16 | Building I Truss Package - BLDG 1 | Material | 496786.6859
17 | Building II Truss Package - BLDG 1 | Material | 499535.2388
|  | Total | 5057414.4488

## SRC-Estimate
Description | Unit | Building Type I | [5 empty] | Building Type II
|  | BLDG 1 | [5 empty] | BLDG 1
|  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Roof | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Roof
Exterior wood stud wall with sheathing | SF | 13143 | 11820 | 13248 | 11460 | 12415 | 1260 | 11100 | 11100 | 11100 | 10920 | 11830 | 1260
House wrap-10'x100' roll size considered | SF | 13143 | 11820 | 13248 | 11460 | 12415 | 1260 | 11100 | 11100 | 11100 | 10920 | 11830 | 1260
Corridor Shear wall sheathing -15/32" plywood | SF | 5775 | 4548 | 4548 | 1380 | 720 |  | 8145 | 6312 | 4740
Demising Shear wall sheathing -15/32" plywood | SF | 15600 | 13920 | 13920 | 9084 | 360 |  | 18660 | 15204 | 14532 | 4200
(2) Densglass in btw framing - Stairs | SF | 2448 | 2244 | 2244 | 2244 | 2244 |  | 2448 | 2244 | 2244 | 2244 | 2244
(2) 1" Gypsum Shaftliners @ Trash Chute | SF |  | 480 | 480 | 480 | 480 |  |  | 480 | 480 | 480 | 480
Unit floor framing : 20" Deep Truss @ 24" OC | SF |  | 20758 | 20465 | 20465 | 20465 |  |  | 20805 | 20805 | 20805 | 20805
Corridor floor framing : 20" Deep Truss @ 24" OC | SF |  | 2845 | 2845 | 2762 | 2762 |  |  | 2645 | 2645 | 2565 | 2565
Balcony floor framing : Pre-fab @ 24"OC | SF |  | 830 | 1341 | 1341 | 1341 |  |  | 1435 | 1435 | 1435 | 1435
L Shaped Balcony floor framing : Pre-fab @ 24"OC | SF |  | 505 | 505 | 505 | 505 |  |  | 182 | 182 | 182 | 182
C Shaped Balcony floor framing : Pre-fab @ 24"OC | SF |  | 172 | 172 | 172 | 172 |  |  | 250 | 250 | 250 | 250
Roof framing : Pre-fab @ 24"OC | SF | [5 empty] | 25365 | [5 empty] | 25330
Draftstopping @ Unit Floor Truss - Plywood (Assumed) | SF |  | 1053 | 1053 | 1053 | 1053 |  |  | 1053 | 1053 | 1053 | 1053
Draftstopping @ Roof Truss - Plywood (Assumed) | SF | [5 empty] | 2085 | [5 empty] | 2070
Balcony Doors | EA |  | 17 | 23 | 23 | 23 |  |  | 23 | 23 | 23 | 23
No of Regular balconies | EA |  | 12 | 18 | 18 | 18 |  |  | 20 | 20 | 20 | 20
No of L Shaped Balconies | EA |  | 3 | 3 | 3 | 3 |  |  | 1 | 1 | 1 | 1
No of C Shaped Balconies | EA |  | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2
Windows Double | EA | 26 | 43 | 55 | 55 | 58 |  | 51 | 56 | 58 | 58 | 55
Windows Single | EA | 16 | 24 | 24 | 24 | 25 |  | 22 | 22 | 22 | 22 | 22
Exterior Entry Doors | EA | 8 | [5 empty] | 6
Patio doors | EA | 17 | [5 empty] | 22
Wood Column Posts | EA | 3 | 3 | 3 | 3 |  |  | 1 | 1 | 1 | 1
Wood Landings | EA | [5 empty] | 9 | [5 empty] | 7
[7 empty] | 343049 | [5 empty] | 333088
GSF | SF | 25197 | 25235 | 25334 | 25346 | 25346 | 126458 | 25375 | 25325 | 25325 | 25325 | 25325 | 126675
Total | [6 empty] | 469507 | [5 empty] | 459763
Their GSF
Difff
[14 empty] | Total GSF | 253133
[14 empty] | Total with GSF | 929270
[14 empty] | Total without GSF | 676137

## SRC-(5) Buyout
Internal Estimate
Description | Company | Type | Unit | Unit cost | Quantity | Total Cost
Layout |  | Labor | SF | 0.3 | 253133 | 75939.9
Framing |  | Labor | SF | 1.2 | 253133 | 303759.6
Floor Truss - Unit - Prefabricated |  | Labor | SF | 1.15 | 165373 | 190178.95
Floor Truss - Corridor - Prefabricated |  | Labor | SF | 1.15 | 21634 | 24879.1
Balcony - Regular - Hand Framed |  | Labor | Each | 500 | 146 | 73000
Balcony - L Shaped - Hand Framed |  | Labor | Each | 600 | 16 | 9600
Balcony - C Shaped - Hand Framed |  | Labor | Each | 600 | 16 | 9600
Stairs - Landings |  | Labor | Each | 300 | 16 | 4800
Roof Truss |  | Labor | SF | 2 | 50695 | 101390
Sheathing - Exterior |  | Labor | SF | 0.3 | 253133 | 75939.9
Shear Wall - Corridor - 15/32 Plywood |  | Labor | Sheets | 11 | 1130.25 | 12432.75
Shear Wall - Demising - 15/32 Plywood |  | Labor | Sheets | 11 | 3296.25 | 36258.75
Fire Wall - Stair Well Shaft - (2) Layers Densglass Btw Framing |  | Labor | Sheets | 20 | 714 | 14280
Fire Wall - Trash Chute - (2) Layers 1" Gypsum Bts Framing |  | Labor | Sheets | 20 | 160 | 3200
Hardware |  | Labor | SF | 0.3 | 253133 | 75939.9
Punchout |  | Labor | SF | 0.25 | 253133 | 63283.25
Nails | Capsol, Inc | Allowance | SF | 0.75 | 253133 | 189849.75
Crane | Capsol, Inc | Allowance | SF | 0.28 | 150000 | 42000
Forklift | Capsol, Inc | Allowance | Months | 8000 | 6 | 48000
Manlift | Capsol, Inc | Allowance | Months | 7000 | 6 | 42000
Fuel | Capsol, Inc | Allowance | Months | 1750 | 6 | 10500
Site Office | Capsol, Inc | Allowance | Months | 1500 | 6 | 9000
Hotels | Capsol, Inc | Allowance | Months | 15000 | 6 | 90000
Site Supervision | Capsol, Inc | Allowance | Month | 18000 | 6 | 108000
|  | Base Cost | 1613831.85
|  | Cost / SF | 6.3754
|  | Markup | 0.25
|  | Sell Price | 2017289.8125
|  | Price / SF | 7.9693
|  | Base Gross Profit | 403457.9625
|  | P/L Margin | 0.2
|  | ROI | 0.25
Buy-Out
Description | Company | Type | Unit | Unit cost | Quantity | Total Cost
Layout |  | Labor | SF | 0.25 | 253133 | 63283.25
Framing |  | Labor | SF | 1.1 | 253133 | 278446.3
Floor Truss - Unit - Prefabricated |  | Labor | SF | 1.1 | 165373 | 181910.3
Floor Truss - Corridor - Prefabricated |  | Labor | SF | 1.1 | 21634 | 23797.4
Balcony - Regular - Hand Framed |  | Labor | Each | 500 | 146 | 73000
Balcony - L Shaped - Hand Framed |  | Labor | Each | 600 | 16 | 9600
Balcony - C Shaped - Hand Framed |  | Labor | Each | 600 | 16 | 9600
Stairs - Landings |  | Labor | Each | 300 | 16 | 4800
Roof Truss |  | Labor | SF | 2 | 50695 | 101390
Sheathing - Exterior |  | Labor | SF | 0.25 | 253133 | 63283.25
Shear Wall - Corridor - 15/32 Plywood |  | Labor | Sheets | 10 | 1130.25 | 11302.5
Shear Wall - Demising - 15/32 Plywood |  | Labor | Sheets | 10 | 3296.25 | 32962.5
Fire Wall - Stair Well Shaft - (2) Layers Densglass Btw Framing |  | Labor | Sheets | 15 | 714 | 10710
Fire Wall - Trash Chute - (2) Layers 1" Gypsum Bts Framing |  | Labor | Sheets | 15 | 160 | 2400
Hardware |  | Labor | SF | 0.25 | 253133 | 63283.25
Punchout |  | Labor | SF | 0.2 | 253133 | 50626.6
Nails | Capsol, Inc | Allowance | SF | 0.65 | 253133 | 164536.45
Crane | Capsol, Inc | Allowance | SF | 50000 | 1 | 42000
Forklift | Capsol, Inc | Allowance | Months | 8000 | 4 | 32000
Manlift | Capsol, Inc | Allowance | Months | 7000 | 4 | 28000
Fuel | Capsol, Inc | Allowance | Months | 1750 | 4 | 7000
Site Office | Capsol, Inc | Allowance | Months | 1500 | 4 | 6000
Hotels | Capsol, Inc | Allowance | Months | 15000 | 4 | 60000
Site Supervision | Capsol, Inc | Allowance | Month | 18000 | 4 | 72000
|  | Base Cost | 1391931.8
|  | Cost / SF | 5.4988 |  | Total Labor Builder Cost | 1391931.8
|  | Sell Price | 2017289.8125 |  | Total Labor Client cost | 2017289.8125
|  | Price / SF | 7.9693 |  | Total Material Builder Cost | 2505150
[5 empty] | Total Material Client cost | 3319502.5
|  | Base Gross Profit | 625358.0125
|  | P/L Margin | 0.31
|  | ROI | 0.44927
Scope - Rough Carpentry | Unit | Rate | Quantity | Cost | Markup | Sell Price | P/L | P/L Margin | SF Price | Waste
Labor Package | SF |  | 253133 | 1391931.8 |  | 2017289.8125 | 625358.0125 | 0.31 | 7.9693
Hardware - Material | SF | 0.63208 | 253133 | 160000 |  | 185000 | 25000 | 0.13514 | 0.73084
Lumber - Material | SF | 5.9257 | 253133 | 1500000 |  | 2050000 | 550000 | 0.26829 | 8.0985
Engineered Wood - Material | SF | 0.27653 | 253133 | 70000 |  | 125000 | 55000 | 0.44 | 0.49381 |  | Recived Quote from Zane
Truss Package - Material | SF | 2.6942 | 253133 | 682000 |  | 805000 | 123000 | 0.1528 | 3.1801 |  | Recived Quote from Zane
Building Wrap - Labor | Each | 150 | 121 | 18150 | 0.35 | 24502.5 | 6352.5 | 0.25926 | 0.096797
Building Wrap - Material | SF | 0.29629 | 253133 | 75000 |  | 130000 | 55000 | 0.42308 | 0.51356
Total |  |  |  | 3897081.8 |  | 5336792.3125 | 1439710.5125 | 0.26977
Add Options | Unit | Rate | Quantity | Cost | Markup | Sell Price | P/L | P/L Margin | SF Price | Waste
Temporary Stair (Single) - Labor & Material | TA | 6000 | 1 | 6000 |  | 8000 | 2000 | 0.25
Hardware - Survey & Oversee Wetset Hardware | TA | 7000 | 1 | 7000 |  | 10500 | 3500 | 0.33333
Textura Payment System | TA | 5000 | 1 | 5000 |  | 5000 | 0 | 0
Total |  |  |  | 18000 |  | 23500 | 5500 | 0.23404
5360292.3125
#REF!
#REF!