## Schedule
PROJECT SCHEDULE — Willow way village
Activity ID | Activity Name | Building | Level | Activity Type | Duration (Days) | Planned Start | Planned Finish | Baseline Start | Baseline Finish | Actual Start | Actual Finish | % Complete | Float (Days) | Status | Builder Cost | Client Price | Profit | Profit % | Predecessor IDs | Material Types | Notes
A0001 | Building VA (North) - Layout - Labor | Building VA (North) |  | 101 - Layout - Labor | 5 | 2026-05-18 | 2026-05-23 | 2026-05-18 | 2026-05-23 | 2026-05-18 | 2026-05-18 | 100% | 0 | Complete | 8132.22 | 10571.89 | 2439.67 | 23.08%
A0002 | Building VA (North) - Framing - Labor | Building VA (North) |  | 102 - Framing - Labor | 2 | 2026-05-24 | 2026-05-26 | 2026-05-23 | 2026-06-19 | 2026-05-25 | 2026-05-18 | 100% | 24 | Complete | 33884.25 | 41780.1 | 7895.85 | 18.9% | A0001
A0003 | Building VA (North) - Sheathing - Labor | Building VA (North) |  | 103 - Sheathing - Labor | 5 | 2026-05-27 | 2026-06-01 | 2026-06-19 | 2026-06-25 | 2026-06-10 | 2026-05-18 | 100% | 24 | Complete | 7506.85 | 9008.22 | 1501.37 | 16.67% | A0002
A0004 | Building VA (North) - Shear Wall - Labor | Building VA (North) |  | 104 - Shear Wall - Labor | 1 | 2026-06-02 | 2026-06-02 | 2026-06-25 | 2026-06-26 |  |  | 0% | 24 | Not Started | 2070 | 2484 | 414 | 16.67% | A0003
A0005 | Building VA (North) - Floor Truss - Labor | Building VA (North) |  | 106 - Floor Truss - Labor | 3 | 2026-06-04 | 2026-06-07 | 2026-06-26 | 2026-07-11 | 2026-06-17 | 2026-05-18 | 100% | 34 | Complete | 19244.38 | 22593.38 | 3349 | 14.82% | A0004
A0006 | Building VA (North) - Roof Truss - Labor | Building VA (North) |  | 107 - Roof Truss - Labor | 8 | 2026-06-09 | 2026-06-17 | 2026-07-11 | 2026-07-29 | 2026-07-02 | 2026-05-18 | 100% | 42 | Complete | 22530 | 25909.5 | 3379.5 | 13.04% | A0005
A0007 | Building VA (North) - Hardware - Labor | Building VA (North) |  | 109 - Hardware - Labor | 4 | 2026-07-05 | 2026-07-09 | 2026-07-29 | 2026-08-04 | 2026-07-20 | 2026-05-18 | 100% | 26 | Complete | 8132.22 | 9352.06 | 1219.84 | 13.04% | A0006
A0008 | Building VA (North) - House Wrap - Labor | Building VA (North) |  | 110 - House Wrap - Labor | 2 | 2026-07-25 | 2026-07-27 | 2026-08-04 | 2026-08-06 | 2026-07-25 | 2026-05-18 | 100% | 10 | Complete | 2697.9 | 3102.59 | 404.69 | 13.04% | A0007
A0009 | Building VA (North) - Stair Labor | Building VA (North) |  | 113 - Stair Labor | 1 | 2026-07-28 | 2026-07-28 | 2026-08-06 | 2026-08-07 | 2026-07-28 | 2026-05-18 | 100% | 10 | Complete | 1800 | 2250 | 450 | 20% | A0008
A0010 | Building VA (North) - Punchout - Labor | Building VA (North) |  | 115 - Punchout - Labor | 5 | 2026-07-29 | 2026-08-03 | 2026-08-07 | 2026-08-13 | 2026-07-29 |  | 39.68% | 10 | In Progress | 6776.85 | 8132.22 | 1355.37 | 16.67% | A0009
A0011 | Building VA (South) - Layout - Labor | Building VA (South) |  | 101 - Layout - Labor | 6 | 2026-05-18 | 2026-05-23 | 2026-05-18 | 2026-05-23 | 2026-05-18 | 2026-05-18 | 100% | 0 | Complete | 8132.22 | 10571.89 | 2439.67 | 23.08%
A0012 | Building VA (South) - Framing - Labor | Building VA (South) |  | 102 - Framing - Labor | 9 | 2026-05-25 | 2026-06-03 | 2026-05-23 | 2026-06-19 | 2026-05-25 | 2026-05-18 | 100% | 16 | Complete | 33884.25 | 41780.1 | 7895.85 | 18.9% | A0011
A0013 | Building VA (South) - Sheathing - Labor | Building VA (South) |  | 103 - Sheathing - Labor | 5 | 2026-06-05 | 2026-06-10 | 2026-06-19 | 2026-06-25 | 2026-06-20 | 2026-05-18 | 100% | 15 | Complete | 6776.85 | 8132.22 | 1355.37 | 16.67% | A0012
A0014 | Building VA (South) - Shear Wall - Labor | Building VA (South) |  | 104 - Shear Wall - Labor | 2 | 2026-06-11 | 2026-06-12 | 2026-06-25 | 2026-06-27 |  |  | 0% | 15 | Not Started | 2800 | 3360 | 560 | 16.67% | A0013
A0015 | Building VA (South) - Floor Truss - Labor | Building VA (South) |  | 106 - Floor Truss - Labor | 13 | 2026-06-29 | 2026-07-13 | 2026-06-27 | 2026-07-13 | 2026-06-29 | 2026-05-18 | 100% | 0 | Complete | 19244.38 | 22593.38 | 3349 | 14.82% | A0014
A0016 | Building VA (South) - Roof Truss - Labor | Building VA (South) |  | 107 - Roof Truss - Labor | 15 | 2026-07-14 | 2026-07-30 | 2026-07-13 | 2026-07-30 | 2026-07-14 | 2026-05-18 | 100% | 0 | Complete | 22530 | 25909.5 | 3379.5 | 13.04% | A0015
A0017 | Building VA (South) - Hardware - Labor | Building VA (South) |  | 109 - Hardware - Labor | 5 | 2026-07-31 | 2026-08-05 | 2026-07-30 | 2026-08-05 | 2026-07-31 | 2026-05-18 | 100% | 0 | Complete | 8132.22 | 9352.06 | 1219.84 | 13.04% | A0016
A0018 | Building VA (South) - House Wrap - Labor | Building VA (South) |  | 110 - House Wrap - Labor | 2 | 2026-08-06 | 2026-08-07 | 2026-08-05 | 2026-08-07 | 2026-08-06 | 2026-05-18 | 100% | 0 | Complete | 2394.6 | 2753.79 | 359.19 | 13.04% | A0017
A0019 | Building VA (South) - Stair Labor | Building VA (South) |  | 113 - Stair Labor | 1 | 2026-08-08 | 2026-08-08 | 2026-08-07 | 2026-08-08 | 2026-08-08 | 2026-05-18 | 100% | 0 | Complete | 1800 | 2250 | 450 | 20% | A0018
A0020 | Building VA (South) - Punchout - Labor | Building VA (South) |  | 115 - Punchout - Labor | 5 | 2026-08-10 | 2026-08-14 | 2026-08-08 | 2026-08-14 | 2026-08-10 | 2026-05-18 | 100% | 0 | Complete | 6776.85 | 8132.22 | 1355.37 | 16.67% | A0019
A0021 | Club house VB (North) - Layout - Labor | Club house VB (North) |  | 101 - Layout - Labor | 1 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-18 | 100% | 0 | Complete | 1445.46 | 1879.1 | 433.64 | 23.08%
A0022 | Club house VB (North) - Framing - Labor | Club house VB (North) |  | 102 - Framing - Labor | 4 | 2026-05-20 | 2026-05-23 | 2026-05-19 | 2026-05-23 | 2026-05-20 | 2026-05-18 | 100% | 0 | Complete | 6022.75 | 7829.58 | 1806.83 | 23.08% | A0021
A0023 | Club house VB (North) - Sheathing - Labor | Club house VB (North) |  | 103 - Sheathing - Labor | 1 | 2026-05-25 | 2026-05-25 | 2026-05-23 | 2026-05-25 | 2026-05-25 | 2026-05-18 | 100% | 0 | Complete | 1204.55 | 1445.46 | 240.91 | 16.67% | A0022
A0024 | Club house VB (North) - Shear Wall - Labor | Club house VB (North) |  | 104 - Shear Wall - Labor | 1 | 2026-05-26 | 2026-05-26 | 2026-05-25 | 2026-05-26 |  |  | 0% | 0 | Not Started | 230 | 276 | 46 | 16.67% | A0023
A0025 | Club house VB (North) - Roof Truss - Labor | Club house VB (North) |  | 107 - Roof Truss - Labor | 8 | 2026-05-27 | 2026-06-04 | 2026-05-26 | 2026-06-04 | 2026-05-27 | 2026-05-18 | 100% | 0 | Complete | 12342 | 14193.3 | 1851.3 | 13.04% | A0024
A0026 | Club house VB (North) - Hardware - Labor | Club house VB (North) |  | 109 - Hardware - Labor | 1 | 2026-06-05 | 2026-06-05 | 2026-06-04 | 2026-06-05 | 2026-06-05 | 2026-05-18 | 100% | 0 | Complete | 1445.46 | 1662.28 | 216.82 | 13.04% | A0025
A0027 | Club house VB (North) - House Wrap - Labor | Club house VB (North) |  | 110 - House Wrap - Labor | 1 | 2026-06-06 | 2026-06-06 | 2026-06-05 | 2026-06-06 |  |  | 0% | 0 | Not Started | 907.5 | 1043.63 | 136.13 | 13.04% | A0026
A0028 | Club house VB (North) - Punchout - Labor | Club house VB (North) |  | 115 - Punchout - Labor | 1 | 2026-06-08 | 2026-06-08 | 2026-06-06 | 2026-06-08 | 2026-06-08 | 2026-05-18 | 100% | 0 | Complete | 1204.55 | 1445.46 | 240.91 | 16.67% | A0027
A0029 | Mail Kiosk (North) - Layout - Labor | Mail Kiosk (North) |  | 101 - Layout - Labor | 1 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-18 | 100% | 0 | Complete | 18.15 | 23.6 | 5.45 | 23.09%
A0030 | Mail Kiosk (North) - Framing - Labor | Mail Kiosk (North) |  | 102 - Framing - Labor | 1 | 2026-05-20 | 2026-05-20 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 2026-05-18 | 100% | 0 | Complete | 75.63 | 90.76 | 15.13 | 16.67% | A0029
A0031 | Mail Kiosk (North) - Sheathing - Labor | Mail Kiosk (North) |  | 103 - Sheathing - Labor | 1 | 2026-05-21 | 2026-05-21 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2026-05-18 | 100% | 0 | Complete | 15.13 | 18.16 | 3.03 | 16.69% | A0030
A0032 | Mail Kiosk (North) - Roof Truss - Labor | Mail Kiosk (North) |  | 107 - Roof Truss - Labor | 1 | 2026-05-22 | 2026-05-22 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-18 | 100% | 0 | Complete | 154 | 177.1 | 23.1 | 13.04% | A0031
A0033 | Mail Kiosk (North) - Hardware - Labor | Mail Kiosk (North) |  | 109 - Hardware - Labor | 1 | 2026-05-23 | 2026-05-23 | 2026-05-22 | 2026-05-23 | 2026-05-23 | 2026-05-18 | 100% | 0 | Complete | 18.15 | 20.87 | 2.72 | 13.03% | A0032
A0034 | Mail Kiosk (North) - Punchout - Labor | Mail Kiosk (North) |  | 115 - Punchout - Labor | 1 | 2026-05-25 | 2026-05-25 | 2026-05-23 | 2026-05-25 |  |  | 0% | 0 | Not Started | 15.13 | 18.16 | 3.03 | 16.69% | A0033
A0035 | Mail Kiosk (South) - Layout - Labor | Mail Kiosk (South) |  | 101 - Layout - Labor | 1 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-18 | 100% | 0 | Complete | 18.15 | 23.6 | 5.45 | 23.09%
A0036 | Mail Kiosk (South) - Framing - Labor | Mail Kiosk (South) |  | 102 - Framing - Labor | 1 | 2026-05-20 | 2026-05-20 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 2026-05-18 | 100% | 0 | Complete | 75.63 | 90.76 | 15.13 | 16.67% | A0035
A0037 | Mail Kiosk (South) - Sheathing - Labor | Mail Kiosk (South) |  | 103 - Sheathing - Labor | 1 | 2026-05-21 | 2026-05-21 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2026-05-18 | 100% | 0 | Complete | 15.13 | 18.16 | 3.03 | 16.69% | A0036
A0038 | Mail Kiosk (South) - Roof Truss - Labor | Mail Kiosk (South) |  | 107 - Roof Truss - Labor | 1 | 2026-05-22 | 2026-05-22 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-18 | 100% | 0 | Complete | 154 | 177.1 | 23.1 | 13.04% | A0037
A0039 | Mail Kiosk (South) - Hardware - Labor | Mail Kiosk (South) |  | 109 - Hardware - Labor | 1 | 2026-05-23 | 2026-05-23 | 2026-05-22 | 2026-05-23 | 2026-05-23 | 2026-05-18 | 100% | 0 | Complete | 18.15 | 20.87 | 2.72 | 13.03% | A0038
A0040 | Mail Kiosk (South) - Punchout - Labor | Mail Kiosk (South) |  | 115 - Punchout - Labor | 1 | 2026-05-25 | 2026-05-25 | 2026-05-23 | 2026-05-25 |  |  | 0% | 0 | Not Started | 15.13 | 18.16 | 3.03 | 16.69% | A0039
A0041 | Trash Enclosure (North) - Layout - Labor | Trash Enclosure (North) |  | 101 - Layout - Labor | 1 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-19 |  |  | 0% | 0 | Not Started | 87.6 | 113.88 | 26.28 | 23.08%
A0042 | Trash Enclosure (North) - Framing - Labor | Trash Enclosure (North) |  | 102 - Framing - Labor | 1 | 2026-05-20 | 2026-05-20 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 69% | 0 | In Progress | 365 | 438 | 73 | 16.67% | A0041
A0043 | Trash Enclosure (North) - Sheathing - Labor | Trash Enclosure (North) |  | 103 - Sheathing - Labor | 1 | 2026-05-21 | 2026-05-21 | 2026-05-20 | 2026-05-21 |  |  | 0% | 0 | Not Started | 73 | 87.6 | 14.6 | 16.67% | A0042
A0044 | Trash Enclosure (North) - Hardware - Labor | Trash Enclosure (North) |  | 109 - Hardware - Labor | 1 | 2026-05-22 | 2026-05-22 | 2026-05-21 | 2026-05-22 |  |  | 0% | 0 | Not Started | 87.6 | 100.74 | 13.14 | 13.04% | A0043
A0045 | Trash Enclosure (North) - Punchout - Labor | Trash Enclosure (North) |  | 115 - Punchout - Labor | 1 | 2026-05-23 | 2026-05-23 | 2026-05-22 | 2026-05-23 |  |  | 0% | 0 | Not Started | 73 | 87.6 | 14.6 | 16.67% | A0044
A0046 | Trash Enclosure (South) - Layout - Labor | Trash Enclosure (South) |  | 101 - Layout - Labor | 1 | 2026-05-18 | 2026-05-19 | 2026-05-18 | 2026-05-19 |  |  | 0% | 0 | Not Started | 87.6 | 113.88 | 26.28 | 23.08%
A0047 | Trash Enclosure (South) - Framing - Labor | Trash Enclosure (South) |  | 102 - Framing - Labor | 1 | 2026-05-20 | 2026-05-20 | 2026-05-19 | 2026-05-20 | 2026-05-20 |  | 69% | 0 | In Progress | 365 | 438 | 73 | 16.67% | A0046
A0048 | Trash Enclosure (South) - Sheathing - Labor | Trash Enclosure (South) |  | 103 - Sheathing - Labor | 1 | 2026-05-21 | 2026-05-21 | 2026-05-20 | 2026-05-21 |  |  | 0% | 0 | Not Started | 73 | 87.6 | 14.6 | 16.67% | A0047
A0049 | Trash Enclosure (South) - Hardware - Labor | Trash Enclosure (South) |  | 109 - Hardware - Labor | 1 | 2026-05-22 | 2026-05-22 | 2026-05-21 | 2026-05-22 |  |  | 0% | 0 | Not Started | 87.6 | 100.74 | 13.14 | 13.04% | A0048
A0050 | Trash Enclosure (South) - Punchout - Labor | Trash Enclosure (South) |  | 115 - Punchout - Labor | 1 | 2026-05-23 | 2026-05-23 | 2026-05-22 | 2026-05-23 |  |  | 0% | 0 | Not Started | 73 | 87.75 | 14.75 | 16.81% | A0049
GRAND TOTAL